## quarterly Progress report
Name of PIA: Harsha Trust
Registration No. of PIA:Registered under Indian Trust Act 211/2002 (Book no-IV, Volume no-5, page-201 to 218)
Project Title: Mahila Kisan Sashakti Karan Pariyojana
Date of PAC approval
Date of Fund release: 28 October 2013
| Reporting Period: January 2014 to March 2014 | To | [9 empty] | From
| Parameters | UoM(Unit of measurement)examples given | Cumulative Target upto the end of previous quarter since inception of project (A') | Progress upto previous reporting period (Up to end of previous quarter since inception of project) (A) | % target achievement till the previous quarter end, since inception | Target for the current quarter (B') | Current Period ( progress for the reporting or current quarter) (B) | % target achievement in the current quarter | Cumulative target till the end of reporting/currently ended quarter (A'+B') | Progress Up to end of reporting period ( cumulative till the end of reporting/ currently ended quarter) (A)+(B) | % achievement of the target [(A+B/A'+B')*100]
1.Outreach
1.1 | No. of Mahila Kisan covered (Castewise): Please give total no. here and the break up below | No. | 550 | 453 | 82.3636 |  | 472 | #DIV/0! |  | 925 | #DIV/0!
1.1.1 | ST |  | 0 | 353 | #DIV/0! | 0 | 303 | #DIV/0! | 0 | 656 | #DIV/0!
1.1.2 | SC |  | 0 | 53 | #DIV/0! | 0 | 55 | #DIV/0! | 0 | 108 | #DIV/0!
1.1.3 | OBC |  | 0 | 47 | #DIV/0! | 0 | 109 | #DIV/0! | 0 | 156 | #DIV/0!
1.1.4 | Minorities |  | 0 | 0 | #DIV/0! | 0 | 5 | #DIV/0! | 0 | 5 | #DIV/0!
1.2 | No. of women farmers trained on atleast one activity covered under MKSP(Castewise): Please Provide total no. and breakup as mentioned below | No. |  | 378 | #DIV/0! |  | 203 | #DIV/0! |  | 581 | #DIV/0!
1.2.1 | ST |  |  | 302 | #DIV/0! | 0 | 136 | #DIV/0! |  | 438 | #DIV/0!
1.2.2 | SC |  |  | 42 | #DIV/0! | 0 | 35 | #DIV/0! |  | 77 | #DIV/0!
1.2.3 | OBCs |  |  | 34 | #DIV/0! | 0 | 31 | #DIV/0! |  | 65 | #DIV/0!
1.2.4 | Minorities |  |  |  | #DIV/0! |  | 1 | #DIV/0! |  | 1 | #DIV/0!
1.3 | No. of women farmers within SHGs trained in at least one of the activities covered. Give Total No. (Provide Breakup in the annexure) | No. | 0 | 0 | #DIV/0! | 0 | 349 | #DIV/0! | 0 | 349 | #DIV/0!
1.3.1 | Sustainable Agriculture |  | 0 | 0 | #DIV/0! | 0 | 349 | #DIV/0! | 0 | 349 | #DIV/0!
1.3.2 | NTFP activity |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! | 0 | 0 | #DIV/0!
1.3.3 | Livestock activity |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! | 0 | 0 | #DIV/0!
1.4 | Interventions at the level of Community Institutions (Please provide data in the manner mentioned below) |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
1.4.4 | No. of SHGs covered |  |  | 54 | #DIV/0! | 0 | 17 | #DIV/0! |  | 71 | #DIV/0!
1.4.5 | No. of Village level Federations covered |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
1.4.6 | No. of Cluster Level/Block level Federations covered |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
1.4.7 | % of the SHGs intervened covered | % |  |  | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
0
1.5 | Livelihood groups: Please give the total no. of Livelihood groups formed and the breakup in the manner mentioned below | No. |  | 10 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 10 | #DIV/0!
1.5.1 | Number of village level Producers'/Collectors' Groups formed |  |  | 10 | #DIV/0! |  | 0 | #DIV/0! |  | 10 | #DIV/0!
1.5.3 | Number of Producer Organisations registered (Give the details with Year of Registration in annexure) |  |  | 0 | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
1.5.4 | Number of SHG members who are part of Producer's/Collector's groups (Please don't double count members) |  |  | 87 | #DIV/0! |  | 0 | #DIV/0! |  | 87 | #DIV/0!
0
1.5 | Geographical coverage: Please provide the details in the manner mentioned below | No. | [5 empty] | #DIV/0! |  | 0 | #DIV/0!
1.5.1 | Revenue Villages |  | 0 | 14 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 14 | #DIV/0!
1.5.2 | No. of Gram Panchayats |  | 0 | 5 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 5 | #DIV/0!
1.5.3 | Number of Blocks |  | 1 | 1 | 100 | 0 | 0 | #DIV/0! | 0 | 1 | #DIV/0!
1.5.4 | Number of Districts |  | 1 | 1 | 100 | 0 | 0 | #DIV/0! | 0 | 1 | #DIV/0!
0
1.6 | Total Agricultural area of Women Farmers in the area of operations (Net cropped area): Please give the total area and the breakup as mentioned below | acre |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
1.6.1 | Net cropped area in acres under Sustainable Agriculture of MKSP owned by Mahila Kisan |  | 0 | 64 | #DIV/0! | 0 | 20.78 | #DIV/0! | 0 | 84.78 | #DIV/0!
1.6.2 | Total agricultural land under Share cropping / lease by the Women Farmers covered under MKSP |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
1.6.3 | Total irrigated area out of the total agricultural area of Women Farmers in the area of operations of PIA under MKSP |  |  | 0 | #DIV/0! | 0 | 3.2 | #DIV/0! |  | 3.2 | #DIV/0!
0
2. Input: | [9 empty] | 0
2.1 | Capacity building: Please provide the informations in the manner mentioned below | [8 empty] | 0
2.1.1 | No. of training modules developed for Mahila Kisan | No. |  | 9 | #DIV/0! | 0 | 0 | #DIV/0! |  | 9 | #DIV/0!
2.1.2 | No. of Training modules developed for Community Resource Persons | No. |  | 9 | #DIV/0! | 0 | 0 | #DIV/0! |  | 9 | #DIV/0!
2.1.3 | No. of training modules developed for Community Para Professionals | No. |  | 2 | #DIV/0! | 0 | 0 | #DIV/0! |  | 2 | #DIV/0!
2.1.4 | No. of days of Capacity building of Mahila Kisan | No. | 0 | 35 | #DIV/0! |  | 9 | #DIV/0! |  | 44 | #DIV/0!
2.1.5 | No. of days of Capacity building of Community Para Professionals | No. | 0 | 1 | #DIV/0! |  | 1 | #DIV/0! |  | 2 | #DIV/0!
2.1.6 | No. of days of Capacity Building of Community Resource persons | No. | 0 | 5 | #DIV/0! |  | 1 | #DIV/0! |  | 6 | #DIV/0!
2.2 | Finances Leveraged- Breakup source wise (Rs. Lakhs): Please provide the break up in the manner mentioned below | [8 empty] | 0
2.2.1 | Credit leveraged from SHG Federations- Both Village Level and Cluster/Block Levels |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
2.2.2 | Credit leveraged from Banks |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
2.2.3 | Funds leveraged from other govt. programs (MGNREGA/RKVY etc) |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
0
2.4 | "Infrastructure & Marketing Fund" for MKSP Funding used as : (Rs. Lakh): Please provide the total fund here utilized and the break up of the funds as mentioned below |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.4.1 | capital investment for common infrastructure/CFC |  |  | 399958 | #DIV/0! |  | 132942 | #DIV/0! |  | 532900 | #DIV/0!
2.4.2 | Capacity building of CRP |  |  | 3280 | #DIV/0! |  | 200 | #DIV/0! |  | 3480 | #DIV/0!
2.4.3 | Capacity building of Community Para Professionals |  |  | 5000 | #DIV/0! |  | 1245 | #DIV/0! |  | 6245 | #DIV/0!
2.4.4 | Capacity building of target women farmers |  |  | 54143 | #DIV/0! |  | 13872 | #DIV/0! |  | 68015 | #DIV/0!
0
2.5 | Physical Assets Created through leveraged funds (to be defined by PIA as provided in Profile): Please define the physical assets created and the value of investment against each of the assets | [8 empty] | 0
2.5.1 | Motor Pump |  | 15 | 2 | 13.3333 |  | 0 | #DIV/0! |  | 2 | #DIV/0!
2.5.2 | Asset 2 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.5.3 | Asset 3 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.5.4 | Asset 4 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.5.5 | Asset 5 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
[5 empty] | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
[5 empty] | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3. Output | Please provide informations in the manner mentioned below, along with the relevant evidences in the annexure | [8 empty] | 0
3.1 | Incremental increase in crop output for the Women Farmers covered under MKSP | Qtls. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.2 | Incremental increase in NTFP collection for Women Farmers covered under MKSP | Qtls. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.3 | Incremental increase in revenue generation for Women Farmers covered by MKSP under sustainable agriculture | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.4 | Incremental increase in revenue generation for Women Farmers covered by MKSP under NTFP activities | Rs. Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5 | Incremental increase in revenue generation for Women Farmers covered by MKSP under Livestock activities | Rs. Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.6 | Gross incremental revenue generation for the livelihood interventions in the area covered | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.7 | Gross incremental revenue generation from the Livelihood interventions per Women Farmer covered | Rs. Lakhs |  |  | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
3.8 | Benckmark productivity level Per acre | Qtls. |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.9 | No. of families meeting benchmark yield for crops grown under SA practices | No. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
0
3.2 | Proportion of Families having Income Range from intervention sunder MKSP: Please provide information in the manner mentioned below | [8 empty] | 0
3.2.1 | < Rs.7500 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.2.2 | Rs 7501-10000 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.2.3 | Rs.10001-15000 |  |  | 280 | #DIV/0! |  | 185 | #DIV/0! |  | 465 | #DIV/0!
3.2.4 | more than Rs.15000 |  |  | 173 | #DIV/0! |  | 287 | #DIV/0! |  | 460 | #DIV/0!
0
3.3 | Average additional foodgrains per family | [8 empty] | 0
3.3.1 | Food Sufficiency | [8 empty] | 0
3.3.1.1 | less than 6 months |  |  | 57 | #DIV/0! |  | 43 | #DIV/0! |  | 100 | #DIV/0!
3.3.1.2 | 7-9 months |  |  | 302 | #DIV/0! |  | 345 | #DIV/0! |  | 647 | #DIV/0!
3.3.1.3 | 9-12 month |  |  | 94 | #DIV/0! |  | 84 | #DIV/0! |  | 178 | #DIV/0!
3.3.1.4 | > 12 months |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
0
3.4 | Social Capital Development | [8 empty] | 0
3.4.1 | Community Resources Persons (Women CRPs only) trained in Sustainable agriculture/NTFP/Livestock practices: Please provide the total no. here and the breakup under each subhead in the annexure | no. |  | 3 | #DIV/0! |  | 1 | #DIV/0! |  | 4 | #DIV/0!
3.4.2 | Community Para Professionals: Please provide the informations in the manner mentioned below |  |  | 3 | #DIV/0! | 0 | 0 | #DIV/0! |  | 3 | #DIV/0!
3.4.2.1 | Women |  |  | 0 | #DIV/0! | 0 |  | #DIV/0! |  | 0 | #DIV/0!
3.4.2.2 | Men |  |  | 3 | #DIV/0! | 0 |  | #DIV/0! |  | 3 | #DIV/0!
0
3.5 | Marketing initiatives: Please provide the informations in the manner mentioned below and relevant evidence in the annexure
3.5.1 | Gross incremental revenue generation from all the crops/products marketed collectively | Rs. lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.2 | Gross Incremental benefit per Women members involved in collective marketing | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.3 | Net returns to the Producer Organizations from Collective marketing | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.4 | Net returns to the Producer Organizations from Value addition | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.5 | No. of women/men involved in Value addition by the Producers' organizations/NTFP collectives/Livestock related collectives | No. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.6 | Mandays/Womendays of work created as a result of value addition activity | No. of days | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.7 | Total amount of wages paid to the workers involved in Value addition activity | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| No. of Value chain studies completed | Nos. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
Note on H11: Compaq: Do mention the date of reporting
Note on H47: User1: 32 no. of functional well in mksp area.

## Summary Phy. quarterly
Sl. No. | Particulars | % achievement of target for the current quarter | % achievement of overall target
1 | Total No. of Mahila Kisan Covered | 472 | #DIV/0!
2 | Total Agricultural area of Mahila Kisan in the area of operations (Net cropped area) | 20.78 | #DIV/0!
4 | No. of Mahila Kisan trained in atleast one activity covered under MKSP | 203 | #DIV/0!
5 | Livelihood groups formed and working | 10 | #DIV/0!
6 | No. of training modules developed for SHG members | 3 | #DIV/0!
7 | No. of Training modules developed for Community Resource Persons | 1 | #DIV/0!
8 | No. of days of Capacity building of women farmers | 9 | #DIV/0!
9 | No. of days of Capacity building of Community Para Professionals | 1 | #DIV/0!
10 | No. of days of Capacity Building of Community Resource persons | 1 | #DIV/0!
11 | Community Resources Persons (Women CRPs only) trained in Sustainable agriculture/NTFP/Livestock practices | 4 | #DIV/0!
12 | Incremental increase in crop output for the Women Farmers covered under MKSP | #DIV/0! | #DIV/0!
13 | Incremental increase in NTFP collection for Women Farmers covered under MKSP | #DIV/0! | #DIV/0!
14 | % of families meeting benchmark yield | #DIV/0! | #DIV/0!
Note on D8: User1: Only in pulses upto 15/7/2014
Note on D12: User1: Module on Pulses pop
Summary sheet: Physical Progress

## Quarterly fin. review-detail
Sl.No | Budget Heads | Total available funds- as per the budget approval for the given year | Total expenditure till the end of previous reporting quarter | Expenditure as % of total available funds- till the end of previous reporting period | Opening balance for the given reporting period | Expenditure in the current quarter | Expenditure as % of opening balance for the quarter | Balance unutilized funds at the end of reporting quarter | Unutilized funds as % of total available funds- approved for the year
1 | Project Inception
1.1 | Mahila Kisan profiling | 1100 | 0 | 0 | 1100 | 0 | 0 | 1100 | 100
1.2 | DPR Preparation | 5000 | 0 | 0 | 5000 | 5500 | 110 | 0 | 0
1.3 | Technical protocols documentation | 5000 | 0 | 0 | 5000 | 0 | 0 | 5000 | 100
1.4 | Value-chain Studies | 0
1.5 | Other (Specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | ….
2 | Institution Building
2.1 | Mobilisation & Promotion of producer groups | 116800 | 25900 | 22 | 90900 | 8420 | 0.09 | 82480 | 77.91
2.2 | Promotion of producer group federation | 0
2.3 | Management support to producer federation | 958000 | 0 | 0 | 958000 | 0 | 0 | 958000 | 100
2.4 | Other (Specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | ….
3 | Capacity Building
3.1 | Training module development : Print | 25000 | 0 | 0 | 25000 | 0 | 0 | 25000 | 100
3.2 | Training module development : audio-visual | 25000 | 0 | 0 | 25000 | 0 | 0
3.3 | Training equipment & material | 75000 | 30120 | 41 | 44000 | 0 | 0 | 44000 | 58.6667
3.4 | Training to CRP | 24000 | 3280 | 13 | 20720 | 200 | 0.96525 | 20520 | 85.5
3.5 | Trainings to para-professionals | 61200 | 5000 | 8.1 | 56200 | 1245 | 2.2153 | 54955 | 89.7958
3.6 | Training to Community | 369100 | 54133 | 14.66 | 314967 | 13872 | 4.4043 | 301095 | 81.5755
3.7 | Training to leaders & PRI | 3800 | 0 | 0 | 3800 | 0 | 0 | 3800 | 100
3.8 | Exposure visits of CRPs to immersion sites | 6000 | 0 | 0 | 6000 | 0 | 0 | 6000 | 100
3.9 | Exposure visit of para-professional to immersion sites | 3200 | 0 | 0 | 3200 | 0 | 0 | 3200 | 100
3.1 | Exposure visit of Community to immersion sites | 15000 | 0 | 0 | 15000 | 0 | 0 | 15000 | 100
3.11 | Service charge to CRP (Excluding the resource fee received by them as trainers) | 180000 | 21000 | 11.66 | 159000 | 24000 | 15.0943 | 135000 | 75
3.12 | Service charge to para-professionals (Excluding the resource fee received by them as trainers) | 67200 | 0 | 0 | 67200 | 12600 | 18.75 | 54600 | 81.25
3.13 | Other (Specify)
3.14 | ….
4 | Community Investment Support
4.1 | Community Infrastructure | 630000 | 399958 | 0 | 230042 | 133900 | 58.2068 | 96142 | 15.2606
4.2 | Inputs to the mahila kisan (grant/subsidy/full loan) | 788500 | 0 | 0 | 788500 | 11660 | 1.4788 | 776840 | 98.5212
4.3 | Inputs to producer groups/ federation (grant/subsidy/full loan) | 0 |  |  | 0 |  | #DIV/0! | 0 | #DIV/0!
4.4 | Operational Fund of Producer federation(Poultry) | 1500000 | 0 | 0 | 1500000 | 0 | 0 | 1500000 | 100
4.5 | Operational Fund of Producer federation | 250000 | 11000 | 4.4 | 239000 |  | 0 | 239000 | 95.6
4.6 | ….
5 | Knowledge Management
5.1 | Identification of best practices | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 100
5.2 | Documentation of best practices | 5000 | 0 | 0 | 5000 | 0 | 0 | 5000 | 100
5.3 | Dissemination of best practices | 5000 | 0 | 0 | 5000 | 0 | 0 | 5000 | 100
5.4 | Other (Specify) |  |  |  | 0
5.5 | ….
6 | Monitoring & Evaluation
6.1 | Baseline survey | 11000 | 4130 | 37 | 6870 | 1200 | 17.4672 | 5670 | 51.5455
6.2 | Endline survey | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0!
6.3 | Independent evaluation studies | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0!
6.4 | Public information disclosure | 15000 | 0 | 0 | 15000 | 4592 | 30.6133 | 10408 | 69.3867
6.5 | Social Audit | 2000 | 0 | 0 | 2000 | 0 | 0 | 2000 | 100
6.6 | Other (Specify)
6.7 | ….
7 | Administration Expenditure (Maximum 5% of total project cost)
7.1 | Staff salaries | 96000 | 16000 | 16.6667 | 80000 | 8000 | 10 | 72000 | 75
7.2 | Travel & conveyance | 42000 | 0 | 0 | 42000 | 3168 | 7.5429 | 38832 | 92.4571
7.3 | Stationary | 24000 | 0 | 0 | 24000 | 1742 | 7.2583 | 22258 | 92.7417
7.4 | Communication | 24000 | 0 | 0 | 24000 | 2309 | 9.6208 | 21691 | 90.3792
| Office Rent | 30000 | 0 | 0 | 30000 | 5000 | 16.6667 | 25000 | 83.3333
7.5 | Other (Specify) |  |  |  | 0 |  | #DIV/0! | 0
7.6 | ….
8 | Grand Total | 5363900 | 570521 | 168.4867 | 4792499 | 237408 | #DIV/0! | 4530591 | #DIV/0!
Note on B1: Compaq: Please fill the heads which are relevant to you at a given point of time according to the timeline submitted by you as per proposal
Note on B3: Compaq: Please provide the total amount here
Note on B9: Compaq: Please add the other relevant fields
Note on B10: Compaq: Please provide the total amount here
Note on B15: Compaq: Please insert the relevant fields here
Note on B16: Compaq: Please provide the total amount here
Note on B30: Compaq: Please insert the relevant fields here
Note on B31: Compaq: Please provide the total amount here.
Note on B37: Compaq: Please insert the relevant fields
Note on B38: Compaq: Please provide the total amount
Note on B43: Compaq: please insert the relevant fields
Note on B44: Compaq: Please give the total amount
Note on B52: Compaq: Please give the total amount
Note on D19: User1: 3100.00 was shown wrongly in the last figure.
Note on D32: User1: 399000 was shown wrongly in the last quarterly report.

## deficit finance
Name of the PIA: Regd. No:
Project Name: Mahila Kisan Sashaktikaran Pariyajana
Date of PAC:
Date of Fund release (Current tranche): 28 October 2013
No. of tranches received:
Total Sanctioned Amount till date:0.241 Lakhs
Total Project Period: 3 Years
Provisional Expenses Statement |  | From:April 2014 |  |  | To:June 2014
Sl.No | Budget Heads | Budget MKSP |  |  |  | Expenditure MKSP |  |  | Variance |  |  | Variance in % |  |  |  | Expenditure Non-MKSP (other ) |  |  | Expenditure Total (all sources) |  |  | % MKSP Funds
|  | Total Budget as per proposal | Up to Previous Reporting Period (A) | Current Period (B) | Up to end of reporting period (A+B)= C | Upto previous Reporting Period (D) | Current Period E | Up to end of reporting period (D+E)= F | Upto end of previous reporting period (A-D)= X | Upto current period (B-E)= G | Upto end of all reporting periods (C-F)= H | Upto the end of previous reporting period ((X/A)*100)= Y | Upto the end of current reporting period ((G/B)*100)=I | Upto the end of all reporting periods ((H/C)*100)=J |  | Upto the end of previous reporting period (K) | Current Period (L) | Up to end of all reporting period (M=K+L) | Upto the end of previous reporting period (N=K+D) | Current Period (O= E+L) | Up to end of all reporting period (P=N+O) | Upto the end of Previous reporting period ((D/N)*100)=Q | Current Period ((E/O)*100)=R | Up to end of reporting period ((F/P)*100)=S
1 | Project Inception | 11000 |  | 0 | 11100 | 0 | 5500 | 5500 | 0 | -5500 | 5600 | #DIV/0! | #DIV/0! | 50.4505 |  |  |  | 0 | 0 | 5500 | 5500 | #DIV/0! | 100 | 100
1.1 | Mahila Kisan profiling | 1100 |  |  | 1100 | 0 | 0 | 0 | 0 | 0 | 1100 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.2 | DPR Preparation | 5000 |  |  | 5000 | 0 | 5500 | 5500 | 0 | -5500 | -500 | #DIV/0! | #DIV/0! | -10 |  |  |  | 0 | 0 | 5500 | 5500 | #DIV/0! | 100 | 100
1.3 | Technical protocols documentation | 5000 |  |  | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.4 | Value-chain Studies | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.5 | Other (Specify) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.6 | …. |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2 | Institution Building | 1074800 |  |  | 1048900 | 25900 | 8420 | 34320 | -25900 | -8420 | 1014580 | #DIV/0! | #DIV/0! | 96.728 |  |  |  | 0 | 25900 | 8420 | 34320 | 100 | 100 | 100
2.1 | Mobilisation & Promotion of producer groups | 116800 |  |  | 90900 | 25900 | 8420 | 34320 | -25900 | -8420 | 56580 | #DIV/0! | #DIV/0! | 62.2442 |  |  |  | 0 | 25900 | 8420 | 34320 | 100 | 100 | 100
2.2 | Promotion of producer group federation | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2.3 | Management support to producer federation | 958000 |  |  | 958000 | 0 | 0 | 0 | 0 | 0 | 958000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2.4 | Other (Specify) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2.5 | …. |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3 | Capacity Building | 854500 |  |  | 740967 | 113533 | 51917 | 165450 | -113533 | -51917 | 575517 | #DIV/0! | #DIV/0! | 77.6711 |  |  |  | 0 | 113533 | 51917 | 165450 | 100 | 100 | 100
3.1 | Training module development : Print | 25000 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.2 | Training module development : audio-visual | 25000 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.3 | Training equipment & material | 75000 |  |  | 44880 | 30120 | 0 | 30120 | -30120 | 0 | 14760 | #DIV/0! | #DIV/0! | 32.8877 |  |  |  | 0 | 30120 | 0 | 30120 | 100 | #DIV/0! | 100
3.4 | Training to CRP | 24000 |  |  | 20720 | 3280 | 200 | 3480 | -3280 | -200 | 17240 | #DIV/0! | #DIV/0! | 83.2046 |  |  |  | 0 | 3280 | 200 | 3480 | 100 | 100 | 100
3.5 | Trainings to para-professionals | 61200 |  |  | 56200 | 5000 | 1245 | 6245 | -5000 | -1245 | 49955 | #DIV/0! | #DIV/0! | 88.8879 |  |  |  | 0 | 5000 | 1245 | 6245 | 100 | 100 | 100
3.6 | Training to Community | 369100 |  |  | 314967 | 54133 | 13872 | 68005 | -54133 | -13872 | 246962 | #DIV/0! | #DIV/0! | 78.4088 |  |  |  | 0 | 54133 | 13872 | 68005 | 100 | 100 | 100
3.7 | Training to leaders & PRI | 3800 |  |  | 3800 | 0 | 0 | 0 | 0 | 0 | 3800 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.8 | Exposure visits of CRPs to immersion sites | 6000 |  |  | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.9 | Exposure visit of para-professional to immersion sites | 3200 |  |  | 3200 | 0 | 0 | 0 | 0 | 0 | 3200 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.1 | Exposure visit of Community to immersion sites | 15000 |  |  | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.11 | Service charge to CRP (Excluding the resource fee received by them as trainers) | 180000 |  |  | 159000 | 21000 | 24000 | 45000 | -21000 | -24000 | 114000 | #DIV/0! | #DIV/0! | 71.6981 |  |  |  | 0 | 21000 | 24000 | 45000 | 100 | 100 | 100
3.12 | Service charge to para-professionals (Excluding the resource fee received by them as trainers) | 67200 |  |  | 67200 | 0 | 12600 | 12600 | 0 | -12600 | 54600 | #DIV/0! | #DIV/0! | 81.25 |  |  |  | 0 | 0 | 12600 | 12600 | #DIV/0! | 100 | 100
3.13 | Other (Specify) |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.14 | …. |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
4 | Community Investment Support | 3418500 |  |  | 3007542 | 410958 | 145560 | 556518 | -410958 | -145560 | 2451024 | #DIV/0! | #DIV/0! | 81.4959 |  |  |  | 0 | 410958 | 145560 | 556518 | 100 | 100 | 100
4.1 | Community Infrastructure | 630000 |  |  | 230042 | 399958 | 133900 | 533858 | -399958 | -133900 | -303816 | #DIV/0! | #DIV/0! | -132.0698 |  |  |  | 0 | 399958 | 133900 | 533858 | 100 | 100 | 100
4.2 | Inputs to the mahila kisan (grant/subsidy/full loan) | 788500 |  |  | 788500 | 0 | 11660 | 11660 | 0 | -11660 | 776840 | #DIV/0! | #DIV/0! | 98.5212 |  |  |  | 0 | 0 | 11660 | 11660 | #DIV/0! | 100 | 100
4.3 | Inputs to producer groups/ federation (grant/subsidy/full loan) | 1500000 |  |  | 1489000 | 11000 | 0 | 11000 | -11000 | 0 | 1478000 | #DIV/0! | #DIV/0! | 99.2612 |  |  |  | 0 | 11000 | 0 | 11000 | 100 | #DIV/0! | 100
4.4 | Operational Fund of Producer federation | 500000 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 500000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
4.5 | Other (Specify) |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
4.6 | …. |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5 | Knowledge Management | 11000 |  |  | 11000 | 0 | 0 | 0 | 0 | 0 | 11000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.1 | Identification of best practices | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.2 | Documentation of best practices | 5000 |  |  | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.3 | Dissemination of best practices | 5000 |  |  | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.4 | Other (Specify) |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.5 | …. |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6 | Monitoring & Evaluation | 28000 |  |  | 23870 | 4130 | 5792 | 9922 | -4130 | -5792 | 13948 | #DIV/0! | #DIV/0! | 58.4332 |  |  |  | 0 | 4130 | 5792 | 9922 | 100 | 100 | 100
6.1 | Baseline survey | 11000 |  |  | 6870 | 4130 | 1200 | 5330 | -4130 | -1200 | 1540 | #DIV/0! | #DIV/0! | 22.4163 |  |  |  | 0 | 4130 | 1200 | 5330 | 100 | 100 | 100
6.2 | Endline survey | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.3 | Independent evaluation studies | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.4 | Public information disclosure | 15000 |  |  | 15000 | 0 | 4592 | 4592 | 0 | -4592 | 10408 | #DIV/0! | #DIV/0! | 69.3867 |  |  |  | 0 | 0 | 4592 | 4592 | #DIV/0! | 100 | 100
6.5 | Social Audit | 2000 |  |  | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | #DIV/0! | #DIV/0! | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.6 | Other (Specify) |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.7 | …. |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
7 | Administration Expenditure (Maximum 5% of total project cost) | 216000 |  |  | 200000 | 16000 | 20219 | 36219 | -16000 | -20219 | 163781 | #DIV/0! | #DIV/0! | 81.8905 |  |  |  | 0 | 16000 | 20219 | 36219 | 100 | 100 | 100
7.1 | Staff salaries | 96000 |  |  | 80000 | 16000 | 8000 | 24000 | -16000 | -8000 | 56000 | #DIV/0! | #DIV/0! | 70 |  |  |  | 0 | 16000 | 8000 | 24000 | 100 | 100 | 100
7.2 | Travel & conveyance | 42000 |  |  | 42000 | 0 | 3168 | 3168 | 0 | -3168 | 38832 | #DIV/0! | #DIV/0! | 92.4571 |  |  |  | 0 | 0 | 3168 | 3168 | #DIV/0! | 100 | 100
7.3 | Stationary | 24000 |  |  | 24000 | 0 | 1742 | 1742 | 0 | -1742 | 22258 | #DIV/0! | #DIV/0! | 92.7417 |  |  |  | 0 | 0 | 1742 | 1742 | #DIV/0! | 100 | 100
7.4 | Communication | 24000 |  |  | 24000 | 0 | 2309 | 2309 | 0 | -2309 | 21691 | #DIV/0! | #DIV/0! | 90.3792 |  |  |  | 0 | 0 | 2309 | 2309 | #DIV/0! | 100 | 100
7.5 | House Rent | 30000 |  |  | 30000 | 0 | 5000 | 5000 | 0 | -5000 | 25000 | #DIV/0! | #DIV/0! | 83.3333 |  |  |  | 0 | 0 | 5000 | 5000 | #DIV/0! | 100 | 100
7.6 | …. |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
8 | Grand Total | 5613800 | 0 | 0 | 5043379 | 570521 | 237408 | 807929 | -570521 | -237408 | 4235450 | #DIV/0! | #DIV/0! | 546.6691 | 0 | 0 | 0 | 0 | 570521 | 237408 | 807929 | #DIV/0! | #DIV/0! | #DIV/0!
| MKSP Fund Balance for the current reporting period | Amount (Rs.) |  | Bank Interest on MKSP Funds |  |  |  |  | Amount (Rs.)
| Opening Balance as on first day of current reporting period | 1885643 |  | Bank Interest Received up to Previous Reporting Period |  |  |  |  | 39414
| Add: Grant Received during the current reporting period | 805580 |  | Bank Interest Received Current Reporting Period |  |  |  |  | 21799
| Add: Bank Interest Received | 21799 |  | Total |  |  |  |  | 61213
| Less: Expenditure during the Current Period | 237408
| Balance as on end of reporting period | 2475614
Note on B61: Compaq: Please give the total amount
Note on B53: Compaq: Please give the total amount
Note on B52: Compaq: please insert the relevant fields
Note on B47: Compaq: Please provide the total amount
Note on B46: Compaq: Please insert the relevant fields
Note on B40: Compaq: Please provide the total amount here.
Note on B39: Compaq: Please insert the relevant fields here
Note on B25: Compaq: Please provide the total amount here
Note on B24: Compaq: Please insert the relevant fields here
Note on B19: Compaq: Please provide the total amount here
Note on B18: Compaq: Please add the other relevant fields
Note on B12: Compaq: Please provide the total amount here
Note on B10: Compaq: Please fill the heads which are relevant to you at a given point of time according to the timeline submitted by you as per proposal
Note on C75: User1: few cheques issued but not clear

## Summary quarterly financial
Financial Progress: Summary
|  |  |  | Cash Inflows |  |  |  | Cash Outflows
Outreach Details |  |  |  | Particulars | MKSP | Other (Please specify. In case of more than one source, mention them seperately by addition of columns) | Total | Particulars | Amount | Expenditure as % of total available funds
Basic Details | Progress till the previous reporting quarter | Progress in the current quarter |  | Opening Balance | 1885643 |  | 1885643 | MKSP | 237408 | 8.7507
Total No. of women farmers covered under MKSP : | 453 | 472 |  | Receipts | 805580 |  | 805580 | Other (Please specify. In case of more than one source, mention them seperately by addition of rows) |  | #DIV/0!
|  |  |  | Bank Interest Earned | 21799 |  | 21799
|  |  |  | Total amount for the quarter | 2713022 | 0 | 2691223 | Total | 237408 | 8.8216
Balance unutilized funds
| Sources of Funds | Unutilized funds | Unutilized funds as % of total available funds for quarter
| MKSP | 2475614 | 91.2493
| Other (Please specify. In case of more than one source, mention them seperately by addition of rows) | 0 | #DIV/0!
| Total | 2475614 | 91.9884
Componentwise break up of the expenditure for the quarter
|  | Broad cost heads for MKSP | Expenditure | Expenditure as % of opening balance for the quarter
|  | Project Inception | 5500 | #DIV/0!
|  | Institution Building | 8420 | #DIV/0!
|  | Capacity Building | 51917 | #DIV/0!
|  | Community Investment Support | 145560 | #DIV/0!
|  | Knowledge Management | 0 | #DIV/0!
|  | Monitoring & Evaluation | 5792 | #DIV/0!
|  | Administration | 20219 | #DIV/0!
Note on F7: User1: Olm fund and Bank interest of Rs 21799

## Summary sheet PIA
Input Indicators
Name of PIA | No of Districts | No. of blocks entered | No. of villages entered | No of Mahila Kisans | No of Mahila Kisans in SHGs | No. of producer groups formed | No of Mahila Kisans in Producers' groups | No. of trainings of Mahila Kisans held | No of days of training given to Mahila Kisan | No. of Mahila Kisans trained | No. of CRPs selected | No. of CRPs trained | No of trainings held for CRP | No of training days for CRP | No. of Training modules developed and conducted | Area of Land under SA (acres) |  | No. of families adopting SA practices | A/V training modules developed for community/CRP training
Harsha Trust | [15 empty] | Khariff | Rabi
1st quarter | 1 | 1 | 50 | 472 |  | 10 | 87 | 9 | 9 | 203 | 3 | 12 | 1 | 1 |  | 64
Best practices identified
Sl. No. | Particulars | Area of activity under MKSP | No. of Mahila Kisan covered under the practice | Benefits accrued to the Mahila Kisan as a result of the practice (in Lakhs) | Remarks
1 |  | WADI | 99 |  | Income start after 4th years
Note on A16: Compaq: Please add rows in case of requirement
Note on E17: Compaq: Applicable only in case of the activities which can have quantifiable outputs. Mention only in case it is applicable
Note on Q6: User1: wadi 100 and pulses 14