## quarterly Progress report
| Name of PIA | Harsha Trust
Project Title:Impacting Livelihood by Farm and Off-farm based Interventions through Women Institutions
Date of PAC approval:28 Oct 2013
| Reporting Period: | To | 2016-09-30 |  | From |  | 2016-07-01
| Parameters | UoM(Unit of measurement) examples given | Total target as per the Sanction order (X) | Plan for the given Financial Year (Y) | Cumulative achievement till last reporting quarter (A) | Achievement in the current reporting quarter Apr-June 2016 (B) | Achievement till date (C=A+B) | % achievement of annual target AT=(C/Y)*100 | % achievement of the total target TT=(C/X)*100
1.Outreach
1.1 | Geographical outreach: Please provide the details in the manner mentioned below | No. |  |  |  |  | 0 | #DIV/0! | #DIV/0!
1.1.1 | Revenue Villages |  | 40 | 25 | 15 | 0 | 15 | 60 | 37.5
1.1.2 | No. of Gram Panchayats |  | 3 | 3 | 5 | 0 | 5 | 166.6667 | 166.6667
1.1.3 | Number of Blocks |  | 1 | 1 | 1 | 0 | 1 | 100 | 100
1.1.4 | Number of Districts |  | 1 | 1 | 1 | 0 | 1 | 100 | 100
1.2 | No. of Mahila Kisan covered (Castewise): Please give total no. here and the break up below | No. | 1750 | 0 | 2235 |  | 2235 | #DIV/0! | 127.7143
1.2.1 | ST |  |  |  | 1593 | 0 | 1593 | #DIV/0! | #DIV/0!
1.2.2 | SC |  |  |  | 291 | 0 | 291 | #DIV/0! | #DIV/0!
1.2.3 | OBC |  |  |  | 337 | 0 | 337 | #DIV/0! | #DIV/0!
1.2.4 | Minorities |  |  |  | 14 | 0 | 14 | #DIV/0! | #DIV/0!
1.3 | No. of Women farmers covered under NRLM compliant SHGs | No. | 1750 | 1750 | 1672 |  | 1672 | 95.5429 | 95.5429
1.3.1 | ST |  |  |  | 1171 | 0 | 1171 | #DIV/0! | #DIV/0!
1.3.2 | SC |  |  |  | 268 | 0 | 268 | #DIV/0! | #DIV/0!
1.3.3 | OBC |  |  |  | 222 | 0 | 222 | #DIV/0! | #DIV/0!
1.3.4 | Minorities |  |  |  | 11 | 0 | 11 | #DIV/0! | #DIV/0!
1.4 | Interventions at the level of Community Institutions (Please provide data in the manner mentioned below) | [5 empty] | 0 | #DIV/0! | #DIV/0!
1.4.1 | No. of SHGs covered |  | 120 | 0 | 129 | 0 | 129 | #DIV/0! | 107.5
1.4.2 | No. of Village level Federations covered |  | 0 |  |  | 0 | 0 | #DIV/0! | #DIV/0!
1.4.3 | No. of Cluster Level/Block level Federations covered |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
1.5 | Livelihood groups: Please give the total no. of Livelihood groups formed and the breakup in the manner mentioned below | No. | 120 | 40 | 10 | 0 | 10 | 25 | 8.3333
1.5.1 | Number of village level Producers'/Collectors' Groups formed |  | 120 | 40 | 10 | 0 | 10 | 25 | 8.3333
1.5.3 | Number of Producer Organisations registered (Give the details with Year of Registration in annexure) |  | 2 | 0 | 2 | 0 | 2 | #DIV/0! | 100
1.5.4 | Number of SHG members who are part of Producer's/Collector's groups (Please don't double count members) |  |  |  |  | 0 | 0 | #DIV/0! | #DIV/0!
2. Landholding under Sustainable Practices
| Total Agricultural area of Women Farmers in the area of operations (Gross cropped area): Owned land+leased/sharecropped land Please give the total area and the breakup as mentioned below | acre |  |  |  |  | 0 | #DIV/0! | #DIV/0!
2.1 | Gross cropped area in acres under Sustainable Agriculture of MKSP owned by Mahila Kisan |  | 1600 |  | 2709.06 | 671 | 3380.06 | #DIV/0! | 211.2538
1.2 | Total agricultural land under Share cropping / lease by the Women Farmers covered under MKSP |  | 100 |  | 74 | 0 | 74 | #DIV/0! | 74
3. Inputs
3.1 Input: Training and Capacity Building
3.1.1 | No. of women farmers trained on MKSP protocols (Castewise): Please Provide total no. and breakup as mentioned below | No. | 1750 | 2235 | 2185 | 851 | 2235 | 100 | 127.7143
3.1.1.1 | ST | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.1.2 | SC | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.1.3 | OBCs | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.1.4 | Minorities | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.2 | No. of trainings conducted under MKSP: For Mahila Kisan | No. | 988 | 652 | 336 | 168 | 504 | 77.3006 | 51.0121
3.1.2.1 | Sustainable Agriculture |  | 844 | 508 | 502 | 57 | 559 | 110.0394 | 66.2322
3.1.2.2 | NTFP activity | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.2.3 | Livestock activity |  | 144 | 144 | 2 | 0 | 2 | 1.3889 | 1.3889
3.1.3 | No. of Trainings conducted under MKSP: For Community Professionals/Para-professionals/Pashu Sakhis | No. | 45 | 20 | 19 | 0 | 19 | 95 | 42.2222
3.1.3.1 | Sustainable Agriculture |  | 35 | 16 | 25 | 1 | 26 | 162.5 | 74.2857
3.1.3.2 | NTFP activity | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.3.3 | Livestock activity |  | 10 | 4 | 1 | 0 | 1 | 25 | 10
3.1.4 | No. of Trainings under MKSP: For Field Functionaries/Field staffs | No. | 9 | 7 | 2 | 0 | 2 | 28.5714 | 22.2222
3.1.4.1 | Sustainable Agriculture |  | 9 | 3 | 1 | 1 | 2 | 66.6667 | 22.2222
3.1.4.2 | NTFP activity | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.4.3 | Livestock activity |  | 0 | 0 |  |  | 0 | #DIV/0! | #DIV/0!
3.1.5 | Capacity building: Please provide the informations in the manner mentioned below | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.1.5.1 | No. of trainee days of Capacity building of Mahila Kisan | No. | 24700 | 16281 | 12647 | 1441 | 14088 | 86.5303 | 57.0364
3.1.5.2 | No. of trainee days of Capacity building of Community Para Professionals | No. | 270 | 197 | 104 | 14 | 118 | 59.8985 | 43.7037
3.1.5.3 | No. of trainee days of Capacity Building of Community Resource persons | No. | 775 | 439 | 424 | 88 | 512 | 116.6287 | 66.0645
3.1.5.4 | No. of Value chain studies completed | Nos. | 2 | 0 | 2 | 0 | 2 | #DIV/0! | 100
3.2 Input: Infrastructure and Marketing fund
"Infrastructure & Marketing Fund" for MKSP Funding used as : (Rs. Lakh): Please provide the total fund here utilized and the break up of the funds as mentioned below
3.2.1 | No. of CFCs developed | No. | [5 empty] | #DIV/0! | #DIV/0!
3.2.2 | capital investment for common infrastructure/CFC | Rs |  |  |  |  | 0 | #DIV/0! | #DIV/0!
3.3 | Physical Assets Created through leveraged funds (to be defined by PIA as provided in Profile): Please define the physical assets created and the value of investment against each of the assets | [5 empty] | 0 | #DIV/0! | #DIV/0!
3.3.1 | Ring well |  | 100 | 0 | 55 |  | 55 | #DIV/0! | 55
3.3.2 | Pump set |  | 10 | 10 | 20 |  | 20 | 200 | 200
3.3.3 | sprayer |  | 25 | 3 | 22 |  | 22 | 733.3333 | 88
3.3.4 | Weeder |  | 50 | 0 | 61 |  | 61 | #DIV/0! | 122
3.3.5 | Bore well ( Convergence) |  | 0 | 15 | 23 |  | 23 | 153.3333 | #DIV/0!
4. Output
Please provide informations in the manner mentioned below, along with the relevant evidences in the annexure
4.1 | Crop output for the Women Farmers covered under MKSP (Please provide the average yield of each crop, in the manner mentioned below) | Qtls. | 16 | 16 | 6.77 |  | 6.77 | 42.3125 | 42.3125
| Paddy | Qtls. | 12 |  | 9.77 | 0 | 9.77 | #DIV/0! | 81.4167
| Horsegram | Qtls. | 4 |  | 2.75 | 0 | 2.75 | #DIV/0! | 68.75
| Cauliflower | Qtls. | 150 |  | 114.29 | 0 | 114.29 | #DIV/0! | 76.1933
| Beans | Qtls. | 25 |  | 37.3 | 0 | 37.3 | #DIV/0! | 149.2
| Brinjal | Qtls. | 100 |  | 0 | 0 | 0 | #DIV/0! | 0
4.2 | No. of women farmers involved in Kitchen garden activities | No. | 0 |  |  |  | 0 | #DIV/0! | #DIV/0!
| ST | No. |  |  | 59 | 0 | 59 | #DIV/0! | #DIV/0!
| SC | No. |  |  | 16 | 0 | 16 | #DIV/0! | #DIV/0!
| Minority | No. |  |  |  |  | 0 | #DIV/0! | #DIV/0!
| Others | No. |  |  | 9 | 0 | 9 | #DIV/0! | #DIV/0!
4.3 | Increase in NTFP collection for Women Farmers covered under MKSP | Qtls. | 0 |  |  |  | 0 | #DIV/0! | #DIV/0!
| Tree 1 | Qtls. | NA |  |  |  | 0 | #DIV/0! | #VALUE!
| Tree 2 | Qtls. | NA |  |  |  | 0 | #DIV/0! | #VALUE!
| Tree 3 | Qtls. | NA |  |  |  | 0 | #DIV/0! | #VALUE!
4A Output: Increase in Income and Food security
4A.1 | Proportion of Families having Income Range from intervention sunder MKSP: Please provide information in the manner mentioned below
4A.1.1 | < Rs.7500 | [5 empty] | 0 | #DIV/0! | #DIV/0!
4A.1.2 | Rs 7501-10000 | [5 empty] | 0 | #DIV/0! | #DIV/0!
4A.1.3 | Rs.10001-15000 |  | 150 | 105 | 45 | 0 | 45 | 42.8571 | 30
4A.1.4 | more than Rs.15000 |  | 1600 | 867 | 1218 | 0 | 1218 | 140.4844 | 76.125
4A.2 | Average additional foodgrains per family
4A.2.1 | Food Sufficiency
4A.2.1.1 | less than 6 months |  | 0 |  |  |  | 0 | #DIV/0! | #DIV/0!
4A.2.1.2 | 7-9 months |  | 0 |  |  |  | 0 | #DIV/0! | #DIV/0!
4A.2.1.3 | 9-12 month |  | 0 |  |  |  | 0 | #DIV/0! | #DIV/0!
4A.2.1.4 | > 12 months |  | 1600 | 1137 | 1098 | 0 | 1098 | 96.5699 | 68.625
4B Output: Creation of Social Capital
4B.1 | Social Capital Development
4B.1.1 | Community Resources Persons (Women CRPs only) trained in Sustainable agriculture/NTFP: Please provide the total no. here and the breakup under each subhead in the annexure | no. | 50 |  | 18 | 1 | 19 | #DIV/0! | 38
4B.1.2 | Community Para Professionals/Pashu Sakhis: Please provide the informations in the manner mentioned below |  | 10 | 0 | 10 | 0 | 10 | #DIV/0! | 100
Note on G36: User4: It includes area coverage by Improve Paddy,Arhar and vegetables
Note on G50: User4: Exposure
Note on G54: User4: Exposure..
Note on E71: User4: It is a target set by the implementing team to cover 60 families.( if Cluster Borewell scheme is available)
Note on D75: User4: Average yield for paddy in koraput is 8 quintal per acre

## Summary Physical-no Fill
Sl. No. | Particulars | Cumulative progress at the end of current quarter | % achievement of annual target | % achievement of overall target
| No. of Revenue villages covered | 15 | 60 | 37.5
1 | Total No. of Mahila Kisan Covered | 2235 | #DIV/0! | 127.7143
2 | No. of Mahila Kisan in NRLM compliant SHGs | 1672 | 95.5429 | 95.5429
3 | Total area brought under Sustainable agriculture practices (acres) | 2234.06 | 421.5208 | 139.6287
4 | No. of Mahila Kisan trained under MKSP | 2185 | 97.7629 | 124.8571
5 | Livelihood groups formed | 10 | 25 | 8.3333
6 | No. of trainee days for Mahila Kisan | 8419 | 99.6331 | 34.085
7 | No. of trainee days for Community Resouce Presons | 336 | 108.3871 | 43.3548
8 | No. of trainee days for Community Para-professionals/Pashu Sakhis | 73 | 81.1111 | 27.037
9 | No.of CRPs trained and deployed | 22 | 44 | 44
10 | No. of Pashu Sakhis trained and Deployed | 10 | #DIV/0! | 100
11 | Increase in crop output for the Women Farmers covered under MKSP | 6.77 | 42.3125 | 42.3125
12 | Incremental increase in NTFP collection for Women Farmers covered under MKSP | NA | NA | NA
Summary sheet: Physical Progress

## Summary Financial
Financial summary for Review at the end of Q2 FY 2016-17
| Total amount received till 31st March 2016 | Expenditure till 30th June 2016 | Closing Balance (as on 30 June 2016) | Total amount received till date in current Financial year (Rs) | Opening balance (as on1st July 2016) | Receipts in the current quarter (July 2016-Sept 2016) | Expenditure in the current quarter (July 2016-Sept 2016) | Closing Balance (as on 30 Sept 2016)
Central share | 8055830 | 7625549.75 | 430280.25 | 0 | 430280.25 | 0 | 333025 | 97255.25
State share | 1611200 | 0 | 1611200 | 0 | 1611200 | 0 | 0 | 1611200
Beneficiary contribution | 0 |  | 0 |  | 0 |  |  | 0
PIA contribution | 0 |  | 0 |  | 0 |  |  | 0
Others(Pls. specify) | 198837.51 | 0 | 198837.51 |  | 198837.51 | 21774.75 | 0 | 220612.26
Total | 9865867.51 | 7625549.75 | 2240317.76 | 0 | 2240317.76 | 21774.75 | 333025 | 1929067.51

## Quaterly Fin.Review Details
Sl.No | Budget Heads | Total available funds- as per the budget approval for the given year | Total expenditure till the end of previous reporting quarter | Expenditure as % of total available funds- till the end of previous reporting period | Opening balance for the given reporting period | Expenditure in the current quarter | Expenditure as % of opening balance for the quarter | Balance unutilized funds at the end of reporting quarter | Unutilized funds as % of total available funds- approved for the year
1 | Project Inception | 113500 | 105500 |  | 8000 | 0 | 0 | 8000 | 7.0485
1.1 | Mahila Kisan profiling | 3500 | 0 | 0 | 3500 |  | 0 | 3500 | 100
1.2 | DPR Preparation | 5000 | 5500 | 110 | -500 |  | 0 | -500 | -10
1.3 | Technical protocols documentation | 5000 | 0 | 0 | 5000 |  | 0 | 5000 | 100
1.4 | Value-chain Studies | 100000 | 100000 | 0 | 0 | 0 | - | 0 | 0
1.5 | Other (Specify) | 0 | 0 | 0 | 0 |  | - | 0 | -
1.6 | …. | 0 | 0 | 0 | 0 | 0 | - |  | -
2 | Institution Building | 1308400 | 728710 |  | 579690 | 30650 | 5.2873 | 549040 | 41.9627
2.1 | Mobilisation & Promotion of producer groups | 350400 | 259815 | 74.1481 | 90585 | 30650 | 33.8356 | 59935 | 17.1047
2.2 | Promotion of producer group federation | 0 | 0 | 0 | 0 |  | - | 0 | -
2.3 | Management support to producer federation | 958000 | 468895 | 48.9452 | 489105 | 0 | 0 | 489105 | 51.0548
2.4 | Other (Specify) | 0 | 0 | 0 | 0 |  | - | 0 | -
2.5 | …. | 0 | 0 | 0 | 0 |  | - |  | -
3 | Capacity Building | 4337400 | 2114211 |  | 2223189 | 249687 | 11.231 | 1973502 | 45.4997
3.1 | Training module development : Print | 25000 | 11250 | 45 | 13750 | 0 | 0 | 13750 | 55
3.2 | Training module development : audio-visual | 25000 | 0 | 0 | 25000 | 0 | 0 | 25000 | 100
3.3 | Training equipment & material | 75000 | 36045 | 48.06 | 38955 | 0 | 0 | 38955 | 51.94
3.4 | Training to CRP | 120000 | 48406 | 40.3383 | 71594 | 6930 | 9.6796 | 64664 | 53.8867
3.5 | Trainings to para-professionals | 183600 | 27120 | 14.7712 | 156480 | 23200 | 14.8262 | 133280 | 72.5926
3.6 | Training to Community | 2334400 | 1004472 | 43.0291 | 1329928 | 120807 | 9.0837 | 1209121 | 51.7958
3.7 | Training to leaders & PRI | 19000 | 6280 | 33.0526 | 12720 | 0 | 0 | 12720 | 66.9474
3.8 | Exposure visits of CRPs to immersion sites | 21000 | 7370 | 35.0952 | 13630 | 0 | 0 | 13630 | 64.9048
3.9 | Exposure visit of para-professional to immersion sites | 11200 | 7268 | 64.8929 | 3932 | 0 | 0 | 3932 | 35.1071
3.1 | Exposure visit of Community to immersion sites | 40000 | 40000 | 100 | 0 | 0 | - | 0 | 0
3.11 | Service charge to CRP (Excluding the resource fee received by them as trainers) | 1080000 | 640000 | 59.2593 | 440000 | 80950 | 18.3977 | 359050 | 33.2454
3.12 | Service charge to para-professionals (Excluding the resource fee received by them as trainers) | 403200 | 286000 | 70.9325 | 117200 | 17800 | 15.1877 | 99400 | 24.6528
3.13 | Other (Specify) | 0 | 0 |  | 0 | 0 | - | 0 | -
3.14 | …. | 0 | 0 |  |  | 0 | - |  | -
4 | Community Investment Support | 6308500 | 4226186.35 |  | 2082313.65 | 7668 | 0.36824 | 2074645.65 | 32.8865
4.1 | Community Infrastructure | 2100000 | 1160150 | 55.2452 | 939850 | 5200 | 0.55328 | 934650 | 44.5071
4.2 | Inputs to the mahila kisan (grant/subsidy/full loan) | 2208500 | 2046901.35 | 92.6829 | 161598.65 | 2468 | 1.5272 | 159130.65 | 7.2054
4.3 | Inputs to producer groups/ federation (grant/subsidy/full loan) | 0 | 0 |  |  | 0 | - |  | -
4.4 | Operational Fund of Producer federation(Poultry) | 1500000 | 852195 | 56.813 | 647805 | 0 | 0 | 647805 | 43.187
4.5 | Operational Fund of Producer federation (cooperative) | 500000 | 166940 | 33.388 | 333060 | 0 | 0 | 333060 | 66.612
4.6 | …. |  | 0 | [5 empty] | -
5 | Knowledge Management | 33000 | 4630 | 14.0303 | 28370 | 0 | 0 | 28370 | 85.9697
5.1 | Identification of best practices | 3000 | 0 | 0 | 3000 | 0 | 0 | 3000 | 100
5.2 | Documentation of best practices | 15000 | 4630 | 30.8667 | 10370 | 0 | 0 | 10370 | 69.1333
5.3 | Dissemination of best practices | 15000 | 0 | 0 | 15000 | 0 | 0 | 15000 | 100
5.4 | Other (Specify) | 0 | 0 |  | 0 | 0 | - | 0 | -
5.5 | …. | 0 | 0 |  |  |  | - |  | -
6 | Monitoring & Evaluation | 147000 | 50091 | 34.0755 | 96909 | 26500 | 27.3452 | 70409 | 47.8973
6.1 | Baseline survey | 35000 | 18960 | 54.1714 | 16040 | 1000 | 6.2344 | 15040 | 42.9714
6.2 | Endline survey | 14000 | 0 |  | 14000 |  | 0 | 14000 | 100
6.3 | Independent evaluation studies | 48000 | 9259 |  | 38741 | 25500 | 65.8217 | 13241 | 27.5854
6.4 | Public information disclosure | 40000 | 21872 | 54.68 | 18128 | 0 | 0 | 18128 | 45.32
6.5 | Social Audit | 10000 | 0 | 0 | 10000 |  | 0 | 10000 | 100
6.6 | Other (Specify) | 0 | 0 |  | 0 |  | - | 0 | -
6.7 | …. | 0 | 0 |  |  |  | - |  | -
7 | Administration Expenditure (Maximum 5% of total project cost) | 648000 | 396221.4 |  | 251778.6 | 18520 | 7.3557 | 233258.6 | 35.9967
7.1 | Staff salaries | 288000 | 200000 | 69.4444 | 88000 | 0 | 0 | 88000 | 30.5556
7.2 | Travel & conveyance | 126000 | 77092.4 | 61.1844 | 48907.6 | 7415 | 15.1612 | 41492.6 | 32.9306
7.3 | Stationary | 72000 | 32211 | 44.7375 | 39789 | 2830 | 7.1125 | 36959 | 51.3319
7.4 | Communication | 72000 | 21918 | 30.4417 | 50082 | 3275 | 6.5393 | 46807 | 65.0097
7.5 | Office Rent | 90000 | 65000 | 72.2222 | 25000 | 5000 | 20 | 20000 | 22.2222
7.6 | …. | 0 | 0 |  |  |  | - |  | -
8 | Grand Total | 12895800 | 7625549.75 |  | 5270250.25 | 333025 | 51.5875 | 4937225.25