## quarterly Progress report
Name of PIA: Harsha Trust
Registration No. of PIA:Registered under Indian Trust Act 211/2002 (Book no-IV, Volume no-5, page-201 to 218)
Project Title: Mahila Kisan Sashakti Karan Pariyojana
Date of PAC approval
Date of Fund release: 28 October 2013
| Reporting Period: January 2014 to March 2014 | To | [9 empty] | From
| Parameters | UoM(Unit of measurement)examples given | Cumulative Target upto the end of previous quarter since inception of project (A') | Progress upto previous reporting period (Up to end of previous quarter since inception of project) (A) | % target achievement till the previous quarter end, since inception | Target for the current quarter (B') | Current Period ( progress for the reporting or current quarter) (B) | % target achievement in the current quarter | Cumulative target till the end of reporting/currently ended quarter (A'+B') | Progress Up to end of reporting period ( cumulative till the end of reporting/ currently ended quarter) (A)+(B) | % achievement of the target [(A+B/A'+B')*100]
1.Outreach
1.1 | No. of Mahila Kisan covered (Castewise): Please give total no. here and the break up below | No. | 550 | 1366 | 248.3636 | 300 | 869 | 289.6667 | 1666 | 2235 | 134.1537
1.1.1 | ST |  | 0 | 965 | #DIV/0! | 0 | 628 | #DIV/0! | 0 | 1593 | #DIV/0!
1.1.2 | SC |  | 0 | 159 | #DIV/0! | 0 | 132 | #DIV/0! | 0 | 291 | #DIV/0!
1.1.3 | OBC |  | 0 | 233 | #DIV/0! | 0 | 104 | #DIV/0! | 0 | 337 | #DIV/0!
1.1.4 | Minorities and Others |  | 0 | 9 | #DIV/0! | 0 | 5 | #DIV/0! | 0 | 14 | #DIV/0!
1.2 | No. of women farmers trained on atleast one activity covered under MKSP(Castewise): Please Provide total no. and breakup as mentioned below | No. | 550 | 904 | 164.3636 | 550 | 614 | 111.6364 | 550 | 1518 | 276
1.2.1 | ST |  |  | 664 | #DIV/0! | 0 | 429 | #DIV/0! |  | 1093 | #DIV/0!
1.2.2 | SC |  |  | 112 | #DIV/0! | 0 | 116 | #DIV/0! |  | 228 | #DIV/0!
1.2.3 | OBCs |  |  | 119 | #DIV/0! | 0 | 67 | #DIV/0! |  | 186 | #DIV/0!
1.2.4 | Minorities and Others |  |  | 9 | #DIV/0! |  | 2 | #DIV/0! |  | 11 | #DIV/0!
1.3 | No. of women farmers within SHGs trained in at least one of the activities covered. Give Total No. (Provide Breakup in the annexure) | No. | 550 | 799 | 145.2727 | 550 | 220 | 40 | 550 | 1019 | 185.2727
1.3.1 | Sustainable Agriculture |  | 550 | 799 | 145.2727 | 550 | 220 | 40 | 550 | 1019 | 185.2727
1.3.2 | NTFP activity |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! | 0 | 0 | #DIV/0!
1.3.3 | Livestock activity |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! | 0 | 0 | #DIV/0!
1.4 | Interventions at the level of Community Institutions (Please provide data in the manner mentioned below) |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
1.4.4 | No. of SHGs covered |  | 40 | 75 | 187.5 | 40 | 40 | 100 | 40 | 115 | 287.5
1.4.5 | No. of Village level Federations covered |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
1.4.6 | No. of Cluster Level/Block level Federations covered |  | 0 | 0 | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
1.4.7 | % of the SHGs intervened covered | % |  |  | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
0
1.5 | Livelihood groups: Please give the total no. of Livelihood groups formed and the breakup in the manner mentioned below | No. | 2 | 10 | 500 | 2 | 0 | 0 | 2 | 10 | 500
1.5.1 | Number of village level Producers'/Collectors' Groups formed |  | 2 | 10 | 500 | 2 | 0 | 0 | 2 | 10 | 500
1.5.3 | Number of Producer Organisations registered (Give the details with Year of Registration in annexure) |  |  | 0 | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
1.5.4 | Number of SHG members who are part of Producer's/Collector's groups (Please don't double count members) |  |  |  | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
0
1.5 | Geographical coverage: Please provide the details in the manner mentioned below | No. | [5 empty] | #DIV/0! |  | 0 | #DIV/0!
1.5.1 | Revenue Villages |  | 15 | 67 | 446.6667 | 15 | 67 | 446.6667 | 15 | 67 | 446.6667
1.5.2 | No. of Gram Panchayats |  | 5 | 5 | 100 | 0 | 0 | #DIV/0! | 0 | 5 | #DIV/0!
1.5.3 | Number of Blocks |  | 1 | 1 | 100 | 0 | 0 | #DIV/0! | 0 | 1 | #DIV/0!
1.5.4 | Number of Districts |  | 1 | 1 | 100 | 0 | 0 | #DIV/0! | 0 | 1 | #DIV/0!
0
1.6 | Total Agricultural area of Women Farmers in the area of operations (Net cropped area): Please give the total area and the breakup as mentioned below | acre |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
1.6.1 | Net cropped area in acres under Sustainable Agriculture of MKSP owned by Mahila Kisan |  | 275 | 560 | 203.6364 | 275 | 75.5 | 27.4545 | 275 | 635.5 | 231.0909
1.6.2 | Total agricultural land under Share cropping / lease by the Women Farmers covered under MKSP |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
1.6.3 | Total irrigated area out of the total agricultural area of Women Farmers in the area of operations of PIA under MKSP |  |  | 8.25 | #DIV/0! | 0 | 0 | #DIV/0! |  | 8.25 | #DIV/0!
0
2. Input: | [9 empty] | 0
2.1 | Capacity building: Please provide the informations in the manner mentioned below | [8 empty] | 0
2.1.1 | No. of training modules developed for Mahila Kisan | No. | 10 | 9 | 90 | 10 | 9 | 90 | 10 | 9 | 90
2.1.2 | No. of Training modules developed for Community Resource Persons | No. | 10 | 9 | 90 | 10 | 9 | 90 | 10 | 9 | 90
2.1.3 | No. of training modules developed for Community Para Professionals | No. | 10 | 2 | 20 | 10 | 9 | 90 | 10 | 9 | 90
2.1.4 | No. of days of Capacity building of Mahila Kisan | No. | 580 | 1473 | 253.9655 | 580 | 1616 | 278.6207 | 580 | 3089 | 532.5862
2.1.5 | No. of days of Capacity building of Community Para Professionals | No. | 20 | 4 | 20 | 20 | 9 | 45 | 20 | 13 | 65
2.1.6 | No. of days of Capacity Building of Community Resource persons | No. | 80 | 38 | 47.5 | 80 | 10 | 12.5 | 80 | 48 | 60
2.2 | Finances Leveraged- Breakup source wise (Rs. Lakhs): Please provide the break up in the manner mentioned below | [8 empty] | 0
2.2.1 | Credit leveraged from SHG Federations- Both Village Level and Cluster/Block Levels |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
2.2.2 | Credit leveraged from Banks |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! | 0 | 0 | #DIV/0!
2.2.3 | Funds leveraged from other govt. programs (MGNREGA/RKVY etc) |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
0
2.4 | "Infrastructure & Marketing Fund" for MKSP Funding used as : (Rs. Lakh): Please provide the total fund here utilized and the break up of the funds as mentioned below |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.4.1 | capital investment for common infrastructure/CFC |  |  |  | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
2.4.2 | Capacity building of CRP |  |  | 4260 | #DIV/0! |  | 11130 | #DIV/0! |  | 15390 | #DIV/0!
2.4.3 | Capacity building of Community Para Professionals |  |  | 1260 | #DIV/0! |  | 1730 | #DIV/0! |  | 2990 | #DIV/0!
2.4.4 | Capacity building of target women farmers |  |  | 69129 | #DIV/0! |  | 118336 | #DIV/0! |  | 187465 | #DIV/0!
0
2.5 | Physical Assets Created through leveraged funds (to be defined by PIA as provided in Profile): Please define the physical assets created and the value of investment against each of the assets | [8 empty] | 0
2.5.1 | Ring Well |  | 30 | 33 | 110 | 0 | 0 | #DIV/0! | 30 | 33 | 110
2.5.2 |  |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.5.3 |  |  |  | 0 | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.5.4 |  |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
2.5.5 |  |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
[5 empty] | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
[5 empty] | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3. Output | Please provide informations in the manner mentioned below, along with the relevant evidences in the annexure | [8 empty] | 0
3.1 | Incremental increase in crop output for the Women Farmers covered under MKSP | Qtls. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.2 | Incremental increase in NTFP collection for Women Farmers covered under MKSP | Qtls. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.3 | Incremental increase in revenue generation for Women Farmers covered by MKSP under sustainable agriculture | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.4 | Incremental increase in revenue generation for Women Farmers covered by MKSP under NTFP activities | Rs. Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5 | Incremental increase in revenue generation for Women Farmers covered by MKSP under Livestock activities | Rs. Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.6 | Gross incremental revenue generation for the livelihood interventions in the area covered | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.7 | Gross incremental revenue generation from the Livelihood interventions per Women Farmer covered | Rs. Lakhs |  |  | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
3.8 | Benckmark productivity level Per acre | Qtls. |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.9 | No. of families meeting benchmark yield for crops grown under SA practices | No. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
0
3.2 | Proportion of Families having Income Range from intervention sunder MKSP: Please provide information in the manner mentioned below | [8 empty] | 0
3.2.1 | < Rs.7500 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.2.2 | Rs 7501-10000 |  |  |  | #DIV/0! |  |  | #DIV/0! |  | 0 | #DIV/0!
3.2.3 | Rs.10001-15000 |  |  | 766 | #DIV/0! |  | 368 | #DIV/0! |  | 1134 | #DIV/0!
3.2.4 | more than Rs.15000 |  |  | 600 | #DIV/0! |  | 501 | #DIV/0! |  | 1101 | #DIV/0!
0
3.3 | Average additional foodgrains per family | [8 empty] | 0
3.3.1 | Food Sufficiency | [8 empty] | 0
3.3.1.1 | less than 6 months |  |  | 145 | #DIV/0! |  | 80 | #DIV/0! |  | 225 | #DIV/0!
3.3.1.2 | 7-9 months |  |  | 847 | #DIV/0! |  | 432 | #DIV/0! |  | 1279 | #DIV/0!
3.3.1.3 | 9-12 month |  |  | 374 | #DIV/0! |  | 357 | #DIV/0! |  | 731 | #DIV/0!
3.3.1.4 | > 12 months |  |  | 0 | #DIV/0! |  | 0 | #DIV/0! |  | 0 | #DIV/0!
0
3.4 | Social Capital Development | [8 empty] | 0
3.4.1 | Community Resources Persons (Women CRPs only) trained in Sustainable agriculture/NTFP/Livestock practices: Please provide the total no. here and the breakup under each subhead in the annexure | no. | 20 | 13 | 65 | 20 | 5 | 25 | 20 | 18 | 90
3.4.2 | Community Para Professionals: Please provide the informations in the manner mentioned below |  | 4 |  | 0 | 4 |  | 0 | 4 |  | 0
3.4.2.1 | Women |  | 0 |  | #DIV/0! | 0 |  | #DIV/0! |  |  | #DIV/0!
3.4.2.2 | Men |  | 4 |  | 0 | 4 |  | 0 | 4 |  | 0
0
3.5 | Marketing initiatives: Please provide the informations in the manner mentioned below and relevant evidence in the annexure
3.5.1 | Gross incremental revenue generation from all the crops/products marketed collectively | Rs. lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.2 | Gross Incremental benefit per Women members involved in collective marketing | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.3 | Net returns to the Producer Organizations from Collective marketing | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.4 | Net returns to the Producer Organizations from Value addition | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.5 | No. of women/men involved in Value addition by the Producers' organizations/NTFP collectives/Livestock related collectives | No. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.6 | Mandays/Womendays of work created as a result of value addition activity | No. of days | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.5.7 | Total amount of wages paid to the workers involved in Value addition activity | Rs Lakhs | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
| No. of Value chain studies completed | Nos. | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
Note on H11: Compaq: Do mention the date of reporting

## Summary Phy. quarterly
Sl. No. | Particulars | % achievement of target for the current quarter | % achievement of overall target
1 | Total No. of Mahila Kisan Covered | 2235 | 134.1537
2 | Total Agricultural area of Mahila Kisan in the area of operations (Net cropped area) | 635.5 | 231.0909
4 | No. of Mahila Kisan trained in atleast one activity covered under MKSP | 1019 | 276
5 | Livelihood groups formed and working | 10 | 500
6 | No. of training modules developed for SHG members | 9 | 90
7 | No. of Training modules developed for Community Resource Persons | 9 | 90
8 | No. of days of Capacity building of women farmers | 3089 | 532.5862
9 | No. of days of Capacity building of Community Para Professionals | 13 | 65
10 | No. of days of Capacity Building of Community Resource persons | 80 | 60
11 | Community Resources Persons (Women CRPs only) trained in Sustainable agriculture/NTFP/Livestock practices | 18 | 90
12 | Incremental increase in crop output for the Women Farmers covered under MKSP | #DIV/0! | #DIV/0!
13 | Incremental increase in NTFP collection for Women Farmers covered under MKSP | #DIV/0! | #DIV/0!
14 | % of families meeting benchmark yield | #DIV/0! | #DIV/0!
Note on D12: User1: Module on Pulses pop
Summary sheet: Physical Progress

## Quarterly fin. review-detail
Sl.No | Budget Heads | Total available funds- as per the budget approval for the given year | Total expenditure till the end of previous reporting quarter | Expenditure as % of total available funds- till the end of previous reporting period | Opening balance for the given reporting period | Expenditure in the current quarter | Expenditure as % of opening balance for the quarter | Balance unutilized funds at the end of reporting quarter | Unutilized funds as % of total available funds- approved for the year
1 | Project Inception | 11100 | 5500 |  | 5600 | 0 | 0 | 5600
1.1 | Mahila Kisan profiling | 1100 | 0 | 0 | 1100 | 0 | 0 | 1100 | 100
1.2 | DPR Preparation | 5000 | 5500 | 110 | -500 | 0 | 0 | -500 | 0
1.3 | Technical protocols documentation | 5000 | 0 | 0 | 5000 | 0 | 0 | 5000 | 100
1.4 | Value-chain Studies | 0 |  | 0 | 0 |  |  | 0
1.5 | Other (Specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | …. |  |  | 0 | 0
2 | Institution Building | 1074800 | 64650 |  | 1010150 | 185207 |  | 824943
2.1 | Mobilisation & Promotion of producer groups | 116800 | 64650 | 55.351 | 52150 | 39435 | 75.6184 | 12715 | 77.91
2.2 | Promotion of producer group federation | 0 |  | 0 | 0 |  |  | 0
2.3 | Management support to producer federation | 958000 | 0 | 0 | 958000 | 145772 | 0 | 812228 | 100
2.4 | Other (Specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | …. |  |  | 0 | 0
3 | Capacity Building | 854500 | 331801 |  | 522699 | 217446 |  | 305253
3.1 | Training module development : Print | 25000 | 0 | 0 | 25000 | 0 | 0 | 25000 | 100
3.2 | Training module development : audio-visual | 25000 | 0 | 0 | 25000 | 0 | 0 | 25000
3.3 | Training equipment & material | 75000 | 30120 | 40.16 | 44880 | 2700 | 0 | 42180 | 56.24
3.4 | Training to CRP | 24000 | 7740 | 32.25 | 16260 | 11130 | 68.4502 | 5130 | 21.375
3.5 | Trainings to para-professionals | 61200 | 7505 | 12.2631 | 53695 | 1730 | 3.2219 | 51965 | 84.9101
3.6 | Training to Community | 369100 | 137134 | 37.1536 | 231966 | 118336 | 51.0144 | 113630 | 30.7857
3.7 | Training to leaders & PRI | 3800 | 0 | 0 | 3800 | 0 | 0 | 3800 | 100
3.8 | Exposure visits of CRPs to immersion sites | 6000 | 6170 | 102.8333 | -170 | 0 | 0 | -170 | -2.8333
3.9 | Exposure visit of para-professional to immersion sites | 3200 | 3268 | 102.125 | -68 | 0 | 0 | -68 | -2.125
3.1 | Exposure visit of Community to immersion sites | 15000 | 15514 | 103.4267 | -514 | 0 | 0 | -514 | -3.4267
3.11 | Service charge to CRP (Excluding the resource fee received by them as trainers) | 180000 | 90750 | 50.4167 | 89250 | 66750 | 74.7899 | 22500 | 12.5
3.12 | Service charge to para-professionals (Excluding the resource fee received by them as trainers) | 67200 | 33600 | 50 | 33600 | 16800 | 50 | 16800 | 25
3.13 | Other (Specify) |  |  |  | 0 |  |  | 0
3.14 | ….
4 | Community Investment Support | 3418500 | 1056258 |  | 2362242 | 467400.5 |  | 1894841.5
4.1 | Community Infrastructure | 630000 | 533858 | 84.7394 | 96142 | 0 | 0 | 96142 | 15.2606
4.2 | Inputs to the mahila kisan (grant/subsidy/full loan) | 788500 | 420250 | 53.2974 | 368250 | 282650.5 | 76.7551 | 85599.5 | 10.856
4.3 | Inputs to producer groups/ federation (grant/subsidy/full loan) | 0
4.4 | Operational Fund of Producer federation(Poultry) | 1500000 | 70150 | 4.6767 | 1429850 | 160350 | 11.2145 | 1269500 | 84.6333
4.5 | Operational Fund of Producer federation (cooperative) | 500000 | 32000 | 6.4 | 468000 | 24400 | 5.2137 | 443600 | 88.72
4.6 | ….
5 | Knowledge Management | 11000 | 0 | 0 | 11000 | 0 | 0 | 11000
5.1 | Identification of best practices | 1000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 100
5.2 | Documentation of best practices | 5000 | 0 | 0 | 5000 | 0 | 0 | 5000 | 100
5.3 | Dissemination of best practices | 5000 | 0 | 0 | 5000 | 0 | 0 | 5000 | 100
5.4 | Other (Specify) |  |  |  | 0 |  |  | 0
5.5 | ….
6 | Monitoring & Evaluation | 28000 | 9922 | 35.4357 | 18078 | 0 | 0 | 18078
6.1 | Baseline survey | 11000 | 5330 | 48.4545 | 5670 | 0 | 0 | 5670 | 51.5455
6.2 | Endline survey | 0 | 0 |  | 0 | 0 |  | 0
6.3 | Independent evaluation studies | 0 | 0 |  | 0 | 0 |  | 0
6.4 | Public information disclosure | 15000 | 4592 | 30.6133 | 10408 | 0 | 0 | 10408 | 69.3867
6.5 | Social Audit | 2000 | 0 | 0 | 2000 | 0 | 0 | 2000 | 100
6.6 | Other (Specify) |  |  |  | 0 |  |  | 0
6.7 | ….
7 | Administration Expenditure (Maximum 5% of total project cost) | 216000 | 96984 |  | 119016 | 50191 |  | 68825
7.1 | Staff salaries | 96000 | 56000 | 58.3333 | 40000 | 24000 | 60 | 16000 | 16.6667
7.2 | Travel & conveyance | 42000 | 13609 | 32.4024 | 28391 | 10745 | 37.8465 | 17646 | 42.0143
7.3 | Stationary | 24000 | 9006 | 37.525 | 14994 | 3892 | 25.957 | 11102 | 46.2583
7.4 | Communication | 24000 | 5869 | 24.4542 | 18131 | 4054 | 22.3595 | 14077 | 58.6542
| Office Rent | 30000 | 12500 | 41.6667 | 17500 | 7500 | 42.8571 | 10000 | 33.3333
7.5 | Other (Specify) |  |  |  | 0 |  |  | 0
7.6 | ….
8 | Grand Total | 5613900 | 1565115 |  | 4048785 | 920244.5 | 0 | 3128540.5
Note on B1: Compaq: Please fill the heads which are relevant to you at a given point of time according to the timeline submitted by you as per proposal
Note on B3: Compaq: Please provide the total amount here
Note on B9: Compaq: Please add the other relevant fields
Note on B10: Compaq: Please provide the total amount here
Note on B15: Compaq: Please insert the relevant fields here
Note on B16: Compaq: Please provide the total amount here
Note on B30: Compaq: Please insert the relevant fields here
Note on B31: Compaq: Please provide the total amount here.
Note on B37: Compaq: Please insert the relevant fields
Note on B38: Compaq: Please provide the total amount
Note on B43: Compaq: please insert the relevant fields
Note on B44: Compaq: Please give the total amount
Note on B52: Compaq: Please give the total amount

## deficit finance
Name of the PIA: Regd. No:
Project Name: Mahila Kisan Sashaktikaran Pariyajana
Date of PAC:
Date of Fund release (Current tranche): 28 October 2013
No. of tranches received:
Total Sanctioned Amount till date:0.241 Lakhs
Total Project Period: 3 Years
Provisional Expenses Statement |  | From:July 2014 |  |  | To:Sept 2014
Sl.No | Budget Heads | Budget MKSP |  |  |  | Expenditure MKSP |  |  | Variance |  |  | Variance in % |  |  |  | Expenditure Non-MKSP (other ) |  |  | Expenditure Total (all sources) |  |  | % MKSP Funds
|  | Total Budget as per proposal | Up to Previous Reporting Period (A) | Current Period (B) | Up to end of reporting period (A+B)= C | Upto previous Reporting Period (D) | Current Period E | Up to end of reporting period (D+E)= F | Upto end of previous reporting period (A-D)= X | Upto current period (B-E)= G | Upto end of all reporting periods (C-F)= H | Upto the end of previous reporting period ((X/A)*100)= Y | Upto the end of current reporting period ((G/B)*100)=I | Upto the end of all reporting periods ((H/C)*100)=J |  | Upto the end of previous reporting period (K) | Current Period (L) | Up to end of all reporting period (M=K+L) | Upto the end of previous reporting period (N=K+D) | Current Period (O= E+L) | Up to end of all reporting period (P=N+O) | Upto the end of Previous reporting period ((D/N)*100)=Q | Current Period ((E/O)*100)=R | Up to end of reporting period ((F/P)*100)=S
1 | Project Inception | 11100 | 5000 | 6100 | 11100 | 5500 | 0 | 5500 | -500 | 6100 | 5600 | -10 | 100 | 50.4505 |  |  |  | 0 | 5500 | 0 | 5500 | 100 | #DIV/0! | 100
1.1 | Mahila Kisan profiling | 1100 | 0 | 1100 | 1100 | 0 | 0 | 0 | 0 | 1100 | 1100 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.2 | DPR Preparation | 5000 | 5000 | 0 | 5000 | 5500 | 0 | 5500 | -500 | 0 | -500 | -10 | #DIV/0! | -10 |  |  |  | 0 | 5500 | 0 | 5500 | 100 | #DIV/0! | 100
1.3 | Technical protocols documentation | 5000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 5000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.4 | Value-chain Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.5 | Other (Specify) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
1.6 | …. |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2 | Institution Building | 1074800 | 34320 | 1040480 | 1074800 | 64650 | 185207 | 249857 | -30330 | 855273 | 824943 | -88.3741 | 82.1999 | 76.7532 |  |  |  | 0 | 64650 | 185207 | 249857 | 100 | 100 | 100
2.1 | Mobilisation & Promotion of producer groups | 116800 | 34320 | 82480 | 116800 | 64650 | 39435 | 104085 | -30330 | 43045 | 12715 | -88.3741 | 52.1884 | 10.8861 |  |  |  | 0 | 64650 | 39435 | 104085 | 100 | 100 | 100
2.2 | Promotion of producer group federation | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2.3 | Management support to producer federation | 958000 | 0 | 958000 | 958000 | 0 | 145772 | 0 | 0 | 812228 | 958000 | #DIV/0! | 84.7837 | 100 |  |  |  | 0 | 0 | 145772 | 145772 | #DIV/0! | 100 | 0
2.4 | Other (Specify) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2.5 | …. |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3 | Capacity Building | 854500 | 165450 | 689050 | 854500 | 331801 | 217446 | 549247 | -166351 | 471604 | 305253 | -100.5446 | 68.4426 | 35.723 |  |  |  | 0 | 331801 | 217446 | 549247 | 100 | 100 | 100
3.1 | Training module development : Print | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.2 | Training module development : audio-visual | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.3 | Training equipment & material | 75000 | 30120 | 44880 | 75000 | 30120 | 2700 | 32820 | 0 | 42180 | 42180 | 0 | 93.984 | 56.24 |  |  |  | 0 | 30120 | 2700 | 32820 | 100 | 100 | 100
3.4 | Training to CRP | 24000 | 3480 | 20520 | 24000 | 7740 | 11130 | 18870 | -4260 | 9390 | 5130 | -122.4138 | 45.7602 | 21.375 |  |  |  | 0 | 7740 | 11130 | 18870 | 100 | 100 | 100
3.5 | Trainings to para-professionals | 61200 | 6245 | 54955 | 61200 | 7505 | 1730 | 9235 | -1260 | 53225 | 51965 | -20.1761 | 96.852 | 84.9101 |  |  |  | 0 | 7505 | 1730 | 9235 | 100 | 100 | 100
3.6 | Training to Community | 369100 | 68005 | 301095 | 369100 | 137134 | 118336 | 255470 | -69129 | 182759 | 113630 | -101.6528 | 60.6981 | 30.7857 |  |  |  | 0 | 137134 | 118336 | 255470 | 100 | 100 | 100
3.7 | Training to leaders & PRI | 3800 | 0 | 3800 | 3800 | 0 | 0 | 0 | 0 | 3800 | 3800 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.8 | Exposure visits of CRPs to immersion sites | 6000 | 0 | 6000 | 6000 | 6170 | 0 | 6170 | -6170 | 6000 | -170 | #DIV/0! | 100 | -2.8333 |  |  |  | 0 | 6170 | 0 | 6170 | 100 | #DIV/0! | 100
3.9 | Exposure visit of para-professional to immersion sites | 3200 | 0 | 3200 | 3200 | 3268 | 0 | 3268 | -3268 | 3200 | -68 | #DIV/0! | 100 | -2.125 |  |  |  | 0 | 3268 | 0 | 3268 | 100 | #DIV/0! | 100
3.1 | Exposure visit of Community to immersion sites | 15000 | 0 | 15000 | 15000 | 15514 | 0 | 15514 | -15514 | 15000 | -514 | #DIV/0! | 100 | -3.4267 |  |  |  | 0 | 15514 | 0 | 15514 | 100 | #DIV/0! | 100
3.11 | Service charge to CRP (Excluding the resource fee received by them as trainers) | 180000 | 45000 | 135000 | 180000 | 90750 | 66750 | 157500 | -45750 | 68250 | 22500 | -101.6667 | 50.5556 | 12.5 |  |  |  | 0 | 90750 | 66750 | 157500 | 100 | 100 | 100
3.12 | Service charge to para-professionals (Excluding the resource fee received by them as trainers) | 67200 | 12600 | 54600 | 67200 | 33600 | 16800 | 50400 | -21000 | 37800 | 16800 | -166.6667 | 69.2308 | 25 |  |  |  | 0 | 33600 | 16800 | 50400 | 100 | 100 | 100
3.13 | Other (Specify) |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3.14 | …. |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
4 | Community Investment Support | 3418500 | 556518 | 2861982 | 3418500 | 1056258 | 467400.5 | 1523658.5 | -499740 | 2394581.5 | 1894841.5 | -89.7976 | 83.6686 | 55.429 |  |  |  | 0 | 1056258 | 467400.5 | 1523658.5 | 100 | 100 | 100
4.1 | Community Infrastructure (ring well) | 630000 | 533858 | 96142 | 630000 | 533858 | 0 | 533858 | 0 | 96142 | 96142 | 0 | 100 | 15.2606 |  |  |  | 0 | 533858 | 0 | 533858 | 100 | #DIV/0! | 100
4.2 | Inputs to the mahila kisan (grant/subsidy/full loan) | 788500 | 11660 | 776840 | 788500 | 420250 | 282650.5 | 702900.5 | -408590 | 494189.5 | 85599.5 | -3504.2024 | 63.6154 | 10.856 |  |  |  | 0 | 420250 | 282650.5 | 702900.5 | 100 | 100 | 100
4.3 | Operational Fund of Producer federation | 1500000 | 0 | 1500000 | 1500000 | 70150 | 160350 | 230500 | -70150 | 1339650 | 1269500 | #DIV/0! | 89.31 | 84.6333 |  |  |  | 0 | 70150 | 160350 | 230500 | 100 | 100 | 100
4.4 | Operational Fund of Producer federation (cooperative) | 500000 | 11000 | 489000 | 500000 | 32000 | 24400 | 56400 | -21000 | 464600 | 443600 | -190.9091 | 95.0102 | 88.72 |  |  |  | 0 | 32000 | 24400 | 56400 | 100 | 100 | 100
4.5 | Other (Specify) |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
4.6 | …. |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5 | Knowledge Management | 11000 | 0 | 11000 | 11000 | 0 | 0 | 0 | 0 | 11000 | 11000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.1 | Identification of best practices | 1000 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 1000 | 1000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.2 | Documentation of best practices | 5000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 5000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.3 | Dissemination of best practices | 5000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 5000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.4 | Other (Specify) |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.5 | …. |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6 | Monitoring & Evaluation | 28000 | 9922 | 18078 | 28000 | 9922 | 0 | 9922 | 0 | 18078 | 18078 | 0 | 100 | 64.5643 |  |  |  | 0 | 9922 | 0 | 9922 | 100 | #DIV/0! | 100
6.1 | Baseline survey | 11000 | 5330 | 5670 | 11000 | 5330 | 0 | 5330 | 0 | 5670 | 5670 | 0 | 100 | 51.5455 |  |  |  | 0 | 5330 | 0 | 5330 | 100 | #DIV/0! | 100
6.2 | Endline survey | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.3 | Independent evaluation studies | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.4 | Public information disclosure | 15000 | 4592 | 10408 | 15000 | 4592 | 0 | 4592 | 0 | 10408 | 10408 | 0 | 100 | 69.3867 |  |  |  | 0 | 4592 | 0 | 4592 | 100 | #DIV/0! | 100
6.5 | Social Audit | 2000 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 2000 | 2000 | #DIV/0! | 100 | 100 |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.6 | Other (Specify) |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6.7 | …. |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
7 | Administration Expenditure (Maximum 5% of total project cost) | 216000 | 36219 | 179781 | 216000 | 96984 | 50191 | 147175 | -60765 | 129590 | 68825 | -167.7711 | 72.0821 | 31.8634 |  |  |  | 0 | 96984 | 50191 | 147175 | 100 | 100 | 100
7.1 | Staff salaries | 96000 | 24000 | 72000 | 96000 | 56000 | 24000 | 80000 | -32000 | 48000 | 16000 | -133.3333 | 66.6667 | 16.6667 |  |  |  | 0 | 56000 | 24000 | 80000 | 100 | 100 | 100
7.2 | Travel & conveyance | 42000 | 3168 | 38832 | 42000 | 13609 | 10745 | 24354 | -10441 | 28087 | 17646 | -329.577 | 72.3295 | 42.0143 |  |  |  | 0 | 13609 | 10745 | 24354 | 100 | 100 | 100
7.3 | Stationary | 24000 | 1742 | 22258 | 24000 | 9006 | 3892 | 12898 | -7264 | 18366 | 11102 | -416.992 | 82.5142 | 46.2583 |  |  |  | 0 | 9006 | 3892 | 12898 | 100 | 100 | 100
7.4 | Communication | 24000 | 2309 | 21691 | 24000 | 5869 | 4054 | 9923 | -3560 | 17637 | 14077 | -154.1793 | 81.3102 | 58.6542 |  |  |  | 0 | 5869 | 4054 | 9923 | 100 | 100 | 100
7.5 | House Rent | 30000 | 5000 | 25000 | 30000 | 12500 | 7500 | 20000 | -7500 | 17500 | 10000 | -150 | 70 | 33.3333 |  |  |  | 0 | 12500 | 7500 | 20000 | 100 | 100 | 100
7.6 | …. |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
8 | Grand Total | 5613900 | 807429 | 4806471 | 5613900 | 1565115 | 920244.5 | 2485359.5 | -757686 | 3886226.5 | 3128540.5 | #DIV/0! | 606.3933 | 414.7834 | 0 | 0 | 0 | 0 | 1565115 | 920244.5 | 2485359.5 | #DIV/0! | #DIV/0! | #DIV/0!
| MKSP Fund Balance for the current reporting period | Amount (Rs.) |  | Bank Interest on MKSP Funds |  |  |  |  | Amount (Rs.)
| Opening Balance as on first day of current reporting period | 1388186.3 |  | Bank Interest Received up to Previous Reporting Period |  |  |  |  | 80168
| Add: Grant Received during the current reporting period | 0 |  | Bank Interest Received Current Reporting Period
| Add: Bank Interest Received |  |  | Total |  |  |  |  | 80168
| Less: Expenditure during the Current Period | 920244.5
| Balance as on end of reporting period | 467941.8
Note on B61: Compaq: Please give the total amount
Note on B53: Compaq: Please give the total amount
Note on B52: Compaq: please insert the relevant fields
Note on B47: Compaq: Please provide the total amount
Note on B46: Compaq: Please insert the relevant fields
Note on B40: Compaq: Please provide the total amount here.
Note on B39: Compaq: Please insert the relevant fields here
Note on B25: Compaq: Please provide the total amount here
Note on B24: Compaq: Please insert the relevant fields here
Note on B19: Compaq: Please provide the total amount here
Note on B18: Compaq: Please add the other relevant fields
Note on B12: Compaq: Please provide the total amount here
Note on B10: Compaq: Please fill the heads which are relevant to you at a given point of time according to the timeline submitted by you as per proposal
Note on C75: User1: few cheques issued but not clear
Note on C71: User1: Tally Balance

## Summary quarterly financial
Financial Progress: Summary
|  |  |  | Cash Inflows |  |  |  | Cash Outflows
Outreach Details |  |  |  | Particulars | MKSP | Other (Please specify. In case of more than one source, mention them seperately by addition of columns) | Total | Particulars | Amount | Expenditure as % of total available funds
Basic Details | Progress till the previous reporting quarter | Progress in the current quarter |  | Opening Balance |  |  | 0 | MKSP | 920244.5 | #DIV/0!
Total No. of women farmers covered under MKSP : | 1366 | 869 |  | Receipts |  |  | 0 | Other (Please specify. In case of more than one source, mention them seperately by addition of rows) |  | #DIV/0!
|  |  |  | Total amount for the quarter | 0 | 0 | 0 | Total | 920244.5 | #DIV/0!
Balance unutilized funds
| Sources of Funds | Unutilized funds | Unutilized funds as % of total available funds for quarter
| MKSP | -920244.5 | #DIV/0!
| Other (Please specify. In case of more than one source, mention them seperately by addition of rows) | 0
| Total | -920244.5 | #DIV/0!
Componentwise break up of the expenditure for the quarter
|  | Broad cost heads for MKSP | Expenditure | Expenditure as % of opening balance for the quarter
|  | Project Inception | 0 | 0
|  | Institution Building | 185207 | 18.3346
|  | Capacity Building | 217446 | 41.6006
|  | Community Investment Support | 467401 | 19.7863
|  | Knowledge Management | 0 | 0
|  | Monitoring & Evaluation | 0 | 0
|  | Administration | 60765 | 51.0562
Note on F7: User1: Bank interest of Rs 18955

## Summary sheet PIA
Input Indicators
Name of PIA | No of Districts | No. of blocks entered | No. of villages entered | No of Mahila Kisans | No of Mahila Kisans in SHGs | No. of producer groups formed | No of Mahila Kisans in Producers' groups | No. of trainings of Mahila Kisans held | No of days of training given to Mahila Kisan | No. of Mahila Kisans trained | No. of CRPs selected | No. of CRPs trained | No of trainings held for CRP | No of training days for CRP | No. of Training modules developed and conducted | Area of Land under SA (acres) |  | No. of families adopting SA practices | A/V training modules developed for community/CRP training
Harsha Trust | [15 empty] | Khariff | Rabi
upto 4th quarter | 1 | 1 | 67 | 2235 | 1547 | 10 | 87 | 152 | 152 | 1518 | 34 | 34 | 13 | 128 | 5 | 560 | 75.5 | 1547 | 1
Best practices identified
Sl. No. | Particulars | Area of activity under MKSP | No. of Mahila Kisan covered under the practice | Benefits accrued to the Mahila Kisan as a result of the practice (in Lakhs) | Remarks
1 |  | WADI | 99 |  | Income start after 4th years
2 |  | Well | 33
Note on A16: Compaq: Please add rows in case of requirement
Note on E17: Compaq: Applicable only in case of the activities which can have quantifiable outputs. Mention only in case it is applicable